## status
Project status tracker
updated on Aug 1 |  |  |  | Schematics |  | Layout
No | Main Component | Sub component | github directory | Owner | Status | Owner | Status | Database unit (0.001) | LVS | DRC
1 | Standard cell | clk_buf_16 | gf180mcu_stdcells | Yutaka KOTANI | Done | - | Done |  | - | -
2 |  | mux2_2 | gf180mcu_stdcells | Yutaka KOTANI | Done | - | Done |  | - | -
3 |  | dffrnq_1 | gf180mcu_stdcells | Yutaka KOTANI | Done | - | Done |  | - | -
4 |  | nand2_1 | gf180mcu_stdcells | Yutaka KOTANI | Done | - | Done |  | - | -
5 | PFD | pfd | pfd | Yutaka KOTANI | Done | Teddy | Done |  | FAIL | PASS
6 | Charge pump | charge_pump | charge_pump | fa_84 | Done | fa_84 | Done | 0.005 | PASS | PASS
7 | VCO | ota_for_vco | ota_for_vco | Yutaka KOTANI | Done | Teddy | Not yet | Not yet | Not yet | Not yet
8 |  | cco | cco | Yutaka KOTANI | Done | Teddy | Ongoing | 0.005 | FAIL | Not yet
9 | Voltage follower | opamp | opamp | Yutaka KOTANI | Done | Teddy | Not yet | Not yet | Not yet | Not yet
10 | Current mirror | current_mirror | current_mirror | Yutaka KOTANI | Done | Teddy | Ongoing |  | Not yet | Not yet
11 | scdac | scdac | scdac | Yutaka KOTANI | Done | Teddy | Ongoing |  | Not yet | Not yet
12 |  | cdac | scdac | Yutaka KOTANI | Done | Teddy | Ongoing |  | Not yet | Not yet
13 |  | bmr | bmr | Yutaka KOTANI | Done | Teddy | Ongoing
14 | shift register | sreg | sreg | Yutaka KOTANI | Done | Yutaka KOTANI | Done |  | PASS | PASS
15 | switch matrix | sw_matrix_25x14 | sw_matrix | Yutaka KOTANI | Done | Yutaka KOTANI | Done |  | PASS | PASS
16 |  | sw_matrix_25x1 | sw_matrix | Yutaka KOTANI | Done | Yutaka KOTANI | Done |  | PASS | PASS
17 |  | sw_matrix_5 | sw_matrix | Yutaka KOTANI | Done | Yutaka KOTANI | Done |  | PASS | PASS
18 |  | sw_matrix_cell | sw_matrix | Yutaka KOTANI | Done | Yutaka KOTANI | Done |  | PASS | PASS
19 |  | trans_gate | trans_gate | Yutaka KOTANI | Done | Yutaka KOTANI | Done |  | PASS | PASS
20 | Integration | c4_all | c4_all | Yutaka KOTANI | Done | Yutaka KOTANI | Ongoing |  | Not yet | Not yet